## Project Description
BAIS Placement System a. ASP.NET Web Application using SQL Server b. Anyone i. View Google mapped internship and full-time placements c. BAIS students login i. Enter internship position/title, company, paid (Y/N), session, responsibilities, skills used and required, contact person ii. Enter full-time position/title, company, session, responsibilities, skills required d. Department System Administrator i. Edit/Add all data

## Actors - Roles
Actor Name | Description
General User | Outside users not logged in
Logged In Student | Any User (student) who is logged in
Sys Admin | Administrator responsible for maintaing all roles and security data and rules within the system

## Iteration 1 Schedule
Total Number of User Stories: |  | 39
Iteration 1 |  |  | Story ID | Story Name | As a... (Actor) | I can... (Goal) | BR
General User ( Not Logged In)
Number of Weeks : | 4 |  | S101 | Home Page | General User | View information on the home page
Start of Iteration: | 2015-02-26 |  | S104 | Create an Account | General User | Create an Account | #1 - Needs to be valid uiowa email
End of Iteration : | 2015-03-26 |  | S105 | Log In | General User | Log in to the system | # 2 - One account per email
Number of User Stories : | 22 |  | S106 | User Friendly Error Page/Message | General User | Receive a user friendly error message when a system error occurs.
|  |  | S108 | Navigation | General User | Use a custom navigation menu that is appropriate for each role
Logged In User (Student)
|  |  | S201 | Home Page | Logged In User | View information on the home page
|  |  | S205 | Add Job | Logged In User | Add Jobs not currently in DB | #1 only 1 current job/internship,
|  |  | S206 | Remove Jobs | Logged In User | Remove listed job | #2 Prompt Confirmation message before deleting job
|  |  | S207 | Update/Edit Job | Logged In User | Update an existing job posting | #3 Prompt Confirmation message before updating job
|  |  | S208 | Account Portal | Logged In User | View Account info and current job postings
|  |  | S209 | Update/Edit User Account | Logged In User | Update their own user account profile information | #4 One account per email
|  |  | S210 | Change Password | Logged In User | Change their own user account password | #5 -Same as uiowa roles, different from previous 3 passwords
|  |  | S212 | Delete User Account | Logged In User | Delete current account | #6 list only up to 4 previous employers
|  |  | S213 | Log Out | Logged In User | Log out from the system
System Admin
|  |  | S301 | Log In | System Admin | Log in to the system as an administrator
|  |  | S302 | Log Out | Logged In User | Log out from the system
|  |  | S303 | Admin Portal/Home Page | System Admin | View informaion and perform administrative functions
|  |  | S307 | System Roles | System Admin | Create and edit ASP.Net Roles
|  |  | S308 | System User Accounts | System Admin | Create and edit ASP.Net User accounts
|  |  | S309 | System Role Access | System Admin | Assign/change each role's functionality access
|  |  | S311 | Add User Profile | System Admin | Add User Profile based upon hawkID | #1 One unique ID will be hawkID (ex: 00075560)
|  |  | S312 | Edit User Profile | System Admin | Edit information on for a specific user
Note on G4: Author: The primary user or stakeholder for the story
Note on H4: Author: The goal that the actor is trying to achieve in the story

## User Stories
Story ID | Story Name | As a... (Actor) | I can... (Goal) | BR
General User ( Not Logged In)
S101 | Home Page | General User | View information on the home page
s102 | Search Jobs | General User | Search for existing jobs
S103 | View Map | General User | View map of job history
S104 | Create an Account | General User | Create an Account | #1 - Needs to be valid uiowa email
S105 | Log In | General User | Log in to the system | # 2 - One account per email
S106 | User Friendly Error Page/Message | General User | Receive a user friendly error message when a system error occurs.
S107 | Common Look & Feel | General User | Have every screen in the system implement a common master page
S108 | Navigation | General User | Use a custom navigation menu that is appropriate for each role
Logged In User (Student)
S201 | Home Page | Logged In User | View information on the home page
S202 | View Map | Logged In User | View map of job history
S203 | Search Jobs | Logged In User | Search for existing jobs
S204 | Search for Company | Logged In User | Search for existing companies
S205 | Add Job | Logged In User | Add Jobs not currently in DB | #1 only 1 current job/internship,
S206 | Remove Jobs | Logged In User | Remove listed job | #2 Prompt Confirmation message before deleting job
S207 | Update/Edit Job | Logged In User | Update an existing job posting | #3 Prompt Confirmation message before updating job
S208 | Account Portal | Logged In User | View Account info and current job postings
S209 | Update/Edit User Account | Logged In User | Update their own user account profile information | #4 One account per email
S210 | Change Password | Logged In User | Change their own user account password | #5 -Same as uiowa roles, different from previous 3 passwords
S211 | Recover password | Logged In User | Recover password
S212 | Delete User Account | Logged In User | Delete current account | #6 list only up to 4 previous employers
S213 | Log Out | Logged In User | Log out from the system
System Admin
S301 | Log In | System Admin | Log in to the system as an administrator
S302 | Log Out | Logged In User | Log out from the system
S303 | Admin Portal/Home Page | System Admin | View informaion and perform administrative functions
S304 | View Map | System Admin | View map of job history
S305 | Search Jobs | System Admin | Search for existing jobs
S306 | Search for Company | System Admin | Search for existing companies
S307 | System Roles | System Admin | Create and edit ASP.Net Roles
S308 | System User Accounts | System Admin | Create and edit ASP.Net User accounts
S309 | System Role Access | System Admin | Assign/change each role's functionality access
S311 | Add User Profile | System Admin | Add User Profile based upon hawkID | #1 One unique ID will be hawkID (ex: 00075560)
S312 | Edit User Profile | System Admin | Edit information on for a specific user
Note on C1: Author: The primary user or stakeholder for the story
Note on D1: Author: The goal that the actor is trying to achieve in the story

## Rough Screen Sketches
Home Page
Search Results
Detailed Job
Add Job
Profile Page